Look West Monitoring Dashboard & Data Workflow — Work Plan

Draft v0.2 — 2026-06-11 · Owner: Mehdi Naji · For review & sign-off by: Jacqueline (Director) · Companion to the [Look West Monitor Two-Pager](./Look_West_Monitor_TwoPager.md)

____________________________________________________________

1. Purpose

This work plan explains how we will gather, validate, organize, and report reliable data to monitor progress under the Look West Strategy. It covers two things side by side: the data workflow (how trustworthy data reaches a single source of truth) and the dashboard workflow (how that data is turned into an executive-friendly monitoring tool and deployed to the people who need it).

The end product is a Look West Monitor dashboard, backed by a governed Look West Data Hub, that lets leadership see at a glance what the strategy committed to, what is moving, where it stands, and where the gaps are — without touching underlying spreadsheets.

2. Current context

The Look West Strategy sets out a hierarchy of goals and targets organized by Stream → Pillar → Theme. Monitoring progress requires a metric (or set of metrics) for each goal, reliable data behind each metric, and a way to report it clearly. Today that data is fragmented across public statistics, internal team spreadsheets, and government announcements, with no single validated source and no executive-facing view of progress. This work plan closes that gap by end of summer.

3. Where we are right now

Data Hub schema designed. A 13-table model exists (Targets, Target Tracker, funding/policy/infrastructure/investment-promotion/major-project trackers, announcements/news, and reference dimensions for Stream/Pillar/Theme/Sector/Region/Timeframe). See look_west_schema.csv.

Dashboard prototype built. An HTML-based Look West Monitor and five tracker subpages exist (dashboards/look_west_tracker/). HTML was chosen over Power BI for flexibility in design, navigation, interactivity, and UX.

Governance scaffolding started. A Workflow and Ownership Registry and Datasets Status table define owners, cadence, and approval state.

Not yet done: metrics are not finalized or leadership-approved; most targets lack validated data; the Hub is not yet populated as the source of truth; and the dashboard is not yet deployed to an internal environment.

4. Proposed approach

Run two parallel tracks that meet at a single connection point — the Data Hub:

Workstream 1 — Data gathering, validation, and Data Hub. Define metrics, source and validate data, and land it in the Hub as the source of truth.

Workstream 2 — Dashboard development, reporting, and deployment. Connect the dashboard to the Hub, report progress, and deploy it securely to executives and authorized users.

Guiding rule — Hub-first. Data flows in one direction: sources → Data Hub → Dashboard. Nothing is typed straight into the dashboard. Every figure shown traces back to a validated, owner-approved row in the Hub. This is why the long pole of the project is sourcing and validating data — not building the page.

Public sources / Internal teams / Announcements
                      |
                      v
          [ Look West Data Hub ]  <-- source of truth (validated)
                      |
                      v
          [ Look West Monitor dashboard ]  --> Executives & authorized users

5. Workstream 1 — Data gathering, validation, and Data Hub

5.1 Data sources (in priority order)

Reliable public data — Statistics Canada, BC Stats, and other credible public sources. Preferred wherever it exists (transparent, repeatable, defensible).

Internal government team data — used when reliable public data is unavailable, or to validate/contextualize public figures.

BC and federal government announcements — used where relevant (e.g., funding commitments, major projects, investment wins).

5.2 From source to Hub — the validation chain

Define the metric for each goal (see §7).

Source the data from the best available source above.

Clean & standardize — align dates (monthly/quarterly), geography (BC / Canada / global), units, and definitions.

Validate with the relevant internal team / SME to confirm accuracy and credibility.

Land in the Hub — record in the appropriate table; update Datasets Status (owner, source, cadence, last updated, approved by).

Flag gaps — where data is missing or weak, mark the target data-gap, add a short qualitative narrative, and log the responsible owner. Nothing is left blank.

5.3 The Data Hub as source of truth

The Hub is the canonical store: governed, owned, and versioned. Each dataset has an Owner + Backup Owner and a Workflow Stage in the Workflow and Ownership Registry, and a cadence in Datasets Status. The dashboard never duplicates data — it reads from the Hub.

5.4 Maintaining the Hub

One agreed format per table (flat tables, one row per record, controlled vocabularies for Stream/Pillar/Theme/Sector).

Refresh on each dataset's stated cadence; manual snapshots are acceptable for the prototype, automation comes later.

Periodic clean-up checkpoint to catch duplicates, stale rows, and broken links between targets and activity records.

6. Workstream 2 — Dashboard development, reporting, and deployment

6.1 What the dashboard reports

The Look West Monitor connects to the Hub and will:

Show progress against targets, goals, and metrics (status, current vs. target, progress %).

Provide an executive summary of overall progress.

Flag missing or weak data coverage explicitly.

Flag areas below expectations (off-track / at-risk).

Show which goals, targets, sectors, or regions need attention.

Include a snapshot of the broader BC economic context.

Help users quickly understand progress, gaps, risks, and next steps.

6.2 Page structure (executive-scannable)

Monitor (executive summary): per-target status, key metric, investment where relevant, owner, data-availability/gap flag.

Targets Tracker: current value, progress % vs. target.

Funding & Investment / Policy & Regulation / Infrastructure / Investment Promotion trackers.

BC economic context snapshot (key public indicators — employment, GDP, exports, investment).

6.3 Technology choice

The dashboard is HTML-based (not Power BI) for flexibility in design, navigation, interactivity, and UX. It reads validated data exported/served from the Hub.

6.4 Deployment (the key bottleneck)

The HTML dashboard must be deployed somewhere secure and accessible to executives and authorized internal users. This requires early coordination with the government IT team on hosting options, authentication/access control, and the data-refresh path. Deployment is started early and in parallel — not left to the end — because IT approvals and provisioning typically drive the critical path.

7. Proposed metrics development process

For every Look West goal/target, we propose one or more practical, reliable metrics. Each proposed metric is documented against the following template, then consulted with internal teams and approved by leadership before it is "locked" in the Hub.

Per-metric template:

| Field | What it captures |
| --- | --- |
| Goal / target | The Look West goal this metric serves (Stream → Pillar → Theme → Target) |
| Metric | What the metric measures |
| Relevance | Why it is meaningful for this specific goal |
| Data exists? | Whether reliable data already exists |
| Public source? | Whether it can come from a public source (StatsCan/BC Stats) |
| Internal input? | Whether internal teams must provide or validate it |
| Update frequency | How often it should be refreshed |
| Limitations / gaps / risks | Known data limitations, gaps, or risks |
| Baseline / target | Starting point and target value, where available |

Process:

Draft metrics for each goal (Mehdi + Daniel) using the template.

Consult internal teams / SMEs to confirm each metric is meaningful, reliable, and feasible.

Revise based on feedback.

Leadership review & approval (Jacqueline) — the formal checkpoint that locks the metric set.

Populate the Hub with approved metrics, baselines, targets, and cadence.

8. Governance, checkpoints, and approvals

| Checkpoint | What is approved | Who | When |
| --- | --- | --- | --- |
| CP1 — Metrics consultation | Internal teams confirm metrics are meaningful/feasible | SMEs / data owners | Short-term |
| CP2 — Leadership metric sign-off | Approved metric set locked into the Hub | Jacqueline | Short-term (gate to scale Hub) |
| CP3 — Data validation | Each dataset validated & marked approved in Datasets Status | Owners / Daniel / Mehdi | Ongoing, per cadence |
| CP4 — Deployment go/no-go | Hosting, access, and refresh path approved | Government IT + Jacqueline | Medium-term |
| CP5 — Executive review | Dashboard meets exec needs; continue/scale | Jacqueline + leadership | End of summer |

Governance is anchored by the Workflow and Ownership Registry (ownership) and Datasets Status (cadence, approval state). No metric is reported, and no dataset is shown, until it has cleared its checkpoint.

9. Engagement pathway with Jacqueline, Daniel, Nathan, and relevant teams

| Person / group | Role in this work | When their input is needed |
| --- | --- | --- |
| Jacqueline (Director / leadership) | Oversight & approval | CP2 metric sign-off; CP4 deployment go/no-go; CP5 executive review |
| Daniel (Analyst) | Data input — sourcing, cleaning, validation into the Hub | Throughout Workstream 1; metric drafting; ongoing refresh |
| Nathan (Technical / IT advice) | Technical advice — hosting, security, deployment path (confirm role) | Early scoping of deployment; CP4; refresh automation |
| Internal teams / SMEs | Provide & validate data; confirm metrics | CP1 consultation; data validation (CP3) |
| Dataset owners (per Registry) | Supply & approve data per cadence | Ongoing per Datasets Status |
| Mehdi (Project lead) | Design, coordination, delivery, narrative | Throughout both workstreams |

Engagement cadence: weekly internal sync (Mehdi + Daniel); biweekly check-ins with dataset owners; early and recurring touchpoints with Nathan / government IT on deployment; scheduled leadership checkpoints at CP2, CP4, CP5.

10. Workflow diagram

Two parallel tracks that meet at the Data Hub, with approval, consultation, validation, deployment, and iteration points marked.

WORKSTREAM 1: DATA                              WORKSTREAM 2: DASHBOARD
 ---------------------------------               ----------------------------------
 Public data (StatsCan, BC Stats)                HTML Monitor prototype (built)
 Internal team data                              Define exec views & flags
 Gov't announcements                                      |
        |                                                 |
        v                                                 |
 Draft metrics per goal -----------------+                |
        |                                |                 |
        v                                |  (early, parallel)
 [CONSULT internal teams / SMEs] <-------+                v
        |                                        [ENGAGE Gov't IT / Nathan]
        v                                         hosting * access * refresh
 [LEADERSHIP APPROVAL - metrics]  (Jacqueline)            |
        |                                                 |
        v                                                 |
 Source + clean + standardize data                        |
        |                                                 |
        v                                                 |
 [VALIDATE data with SMEs]                                |
        |                                                 |
        v                                                 |
 ===========>  [ LOOK WEST DATA HUB ]  <==================+   <- TRACKS CONNECT
               source of truth (validated)               |
                       |                                  |
                       +--------------------------------> Connect dashboard to Hub
                                                          |
                                                          v
                                              Report progress / flag gaps & risks
                                                          |
                                                          v
                                              [DEPLOYMENT GO/NO-GO]  (IT + Jacqueline)
                                                          |
                                                          v
                                              Deploy to executives / authorized users
                                                          |
                                                          v
                                          <===== ITERATE & REFINE (feedback loop) =====>

Reading the diagram: metrics are consulted and approved by leadership before data is mass-sourced; validated data lands in the Hub (the single connection point); the dashboard reads from the Hub; IT engagement runs in parallel from the start so deployment isn't a late surprise; everything loops back through iteration and refinement.

11. Timeline and milestones

Target: process streamlined and dashboard deployed by end of summer. Dates are indicative and anchor to checkpoints rather than fixed calendar days.

| Horizon | Focus | Key outputs | Gates / dependencies |
| --- | --- | --- | --- |
| Immediate (Weeks 1–2) | Lock scope; draft metrics; open IT conversation | Metric drafts per goal (template); confirmed dataset owners; initial IT/deployment scoping with Nathan | — |
| Short-term (Weeks 3–5) | Consult teams; get metrics approved; begin sourcing | CP1 consultation done; CP2 leadership metric sign-off; first validated datasets in Hub | CP2 gates Hub scale-up |
| Medium-term (Weeks 6–9) | Populate Hub; build dashboard against real data; lock deployment path | Hub populated across domains; dashboard wired to Hub; CP4 deployment go/no-go | CP4 depends on IT provisioning |
| End of summer (Weeks 10–12) | Deploy; validate with users; iterate | Dashboard deployed to internal environment; CP5 executive review; refined v1 | Deployment requires CP4 cleared |
| Ongoing | Maintain & refresh | Cadence-based refresh; standing data-gap outreach; move toward automation | — |

Key checkpoints on the timeline: CP1 (consultation) → CP2 (metric approval) → CP3 (rolling data validation) → CP4 (deployment go/no-go) → CP5 (executive review).

12. Data blockers, limitations, and risks

| Bottleneck / risk | Impact | Mitigation |
| --- | --- | --- |
| Finding reliable data for every metric | Some goals may lack a clean metric | Prefer public sources; allow internal/proxy metrics; flag gaps openly with narrative |
| Validating accuracy & credibility | Reporting wrong numbers erodes trust | SME validation step before any figure enters the Hub |
| Timely input from internal teams | Slows sourcing & validation | Owner packets + biweekly check-ins; escalate via leadership if blocked |
| Leadership approval of metrics | Hub scale-up is gated on CP2 | Early consultation so approval is a confirmation, not a debate |
| Maintaining a clean Hub | Drift, duplicates, stale data | Controlled vocabularies, ownership, periodic clean-up checkpoint |
| Connecting Hub to dashboard | Manual refresh is brittle | Define a simple, repeatable export/serve path; automate in a later phase |
| Deploying the HTML dashboard (key bottleneck) | Executives can't access it | Engage government IT early (parallel track); resolve hosting/auth at CP4 |
| Keeping the dashboard updated | Decisions made on stale data | Cadence in Datasets Status; move from manual snapshots to scheduled refresh |

13. Immediate next steps

Confirm dataset owners from the Workflow and Ownership Registry.

Draft metrics for each Look West goal using the §7 template (Mehdi + Daniel).

Open the deployment conversation with Nathan / government IT (hosting, access, refresh) — start in parallel now.

Schedule the metrics consultation (CP1) with internal teams/SMEs.

Book the leadership metric sign-off (CP2) with Jacqueline.

Stand up the cadence: weekly internal sync + biweekly owner check-ins.