## CONFIG
key | value | description
sector_name | BC Tourism | Display name for the sector
province | British Columbia | Full province name
province_abbr | BC | Province abbreviation
strategy_name | Look West Strategy | Strategy being tracked
strategy_year | 2030 | Target year
dashboard_title | B.C. Tourism Sector Dashboard | Main title
dashboard_subtitle | Look West Strategy · 2030 Target Monitoring | Subtitle
last_updated | 2026-04-07 | Date of most recent update
internal_only | TRUE | Internal document flag
accent_color | #0D9488 | Primary accent colour

## SECTOR_STRUCTURE
record_type | sector_id | subsector_id | subsector_name | naics_4digit | naics_5digit | tab_order | show_as_tab | dashboard_color | has_reliable_data | data_availability_note | heading | body_text | caveat | last_updated | source_tier | confidence_tag
sector | tourism | ALL | BC Tourism |  |  | 0 | TRUE | #0D9488 | TRUE |  | What is the BC Tourism Sector? | The British Columbia tourism sector encompasses all businesses and activities involved in attracting and serving visitors to the province. BC is Canada's second-most-visited province, welcoming over 8 million non-resident visitors in 2025. The sector spans accommodation, food & beverage, transportation, recreation, attractions, and travel trade. Tourism generates over $23 billion in annual revenue and directly employs more than 113,000 workers, representing approximately 4.5% of BC's total workforce. The sector is a critical driver of regional economies, particularly in smaller communities and rural areas. | Data combines Statistics Canada Table 24-10-0055-01 (visitor arrivals) and BC Stats Tourism Economic Accounts (2024). Live indicators refresh from source APIs. | 2026-04-07 | official-curated | high
subsector | tourism | ACCOM | Accommodation & Hotels | 7211 | 72111 | 1 | TRUE | #0891B2 | TRUE | Includes hotels, motels, resorts, B&Bs, short-term rentals. Data from MRDT room revenue filings.
subsector | tourism | TRANSPORT | Transportation | 4811 | 48111 | 2 | TRUE | #2563EB | TRUE | Air passenger traffic (YVR/YYJ), BC Ferries vehicle & passenger volumes, land border crossings.
subsector | tourism | FOODBEV | Food & Beverage | 7225 | 72251 | 3 | TRUE | #D97706 | TRUE | Accommodation & food services employment, food services receipts (BC vs. Canada index).
subsector | tourism | RECR | Recreation & Attractions | 7131 | 71311 | 4 | TRUE | #7C3AED | TRUE | Tourism establishments by region and size category, employment by tourism region.

## STRATEGY_GOALS
goal_id | goal_name | pillar | rag_status | progress_pct | target_value | target_unit | target_year | baseline_year | baseline_value | related_subsectors
T-G01 | Grow tourism GDP to $10B (real 2017$) by 2030 | Economic Growth | GREEN | 79 | 10000 | millions_cad_2017 | 2030 | 2019 | 8307 | ALL
T-G02 | Recover and exceed 2019 international overnight visitor levels by 2026 | Visitor Growth | AMBER | 72 | 5.5 | million visitors | 2026 | 2019 | 4.8 | ALL
T-G03 | Increase tourism sector employment to 130,000 FTE by 2028 | Workforce | GREEN | 88 | 130000 | FTE | 2028 | 2019 | 137140 | ALL
T-G04 | Grow total room revenue province-wide to $6B annually by 2028 | Accommodation | GREEN | 79 | 6000 | millions_cad | 2028 | 2019 | 3234 | ACCOM
T-G05 | Double trans-Pacific air seat capacity through YVR by 2030 | Air Access | AMBER | 54 | 2 | x_multiplier | 2030 | 2019 | 1 | TRANSPORT
T-G06 | Achieve Indigenous tourism revenue parity with 2019 by 2027 and grow 20% by 2030 | Indigenous Tourism | AMBER | 61 | 1.2 | x_multiplier | 2030 | 2019 | 1 | RECR
T-G07 | Grow food services receipts to $12B annually by 2030 (indexed to 2010) | Food & Beverage | GREEN | 85 | 12000 | millions_cad | 2030 | 2010 | 4200 | FOODBEV
T-G08 | Secure 3 new scheduled international air routes to underserved markets | Air Access | RED | 33 | 3 | new routes | 2028 | 2024 | 0 | TRANSPORT

## INITIATIVE_TRACKER
initiative_id | initiative_name | pillar | rag_status | status | progress_pct | owner_ministry | next_milestone | next_milestone_date | last_review_date | related_subsectors | description
T-I01 | Destination BC International Marketing Campaign 2025–2030 | Visitor Growth | GREEN | Active | 75 | Ministry of Tourism, Arts, Culture & Sport | Publish Q2 2026 campaign analytics report | 2026-06-30 | 2026-03-15 | ALL | Multi-market campaign targeting UK, Australia, Japan, and Germany to rebuild post-COVID international visitor volumes. Budget: $28M over 5 years.
T-I02 | BC Tourism Labour Strategy Phase II — Workforce Retention | Workforce | AMBER | Active | 55 | Ministry of Labour / TACS | Launch regional workforce hubs in 3 communities | 2026-09-30 | 2026-02-20 | ALL | Address critical hospitality and food-services labour shortages through targeted immigration pathways, upskilling programs, and seasonal worker pilots.
T-I03 | Sustainable Tourism Infrastructure Fund | Economic Growth | GREEN | Active | 70 | Ministry of Tourism, Arts, Culture & Sport | Announce Round 3 grant recipients | 2026-07-15 | 2026-03-01 | ACCOM¦RECR | $45M fund to support sustainable tourism infrastructure upgrades including trail networks, visitor centres, EV charging, and climate-resilient facilities.
T-I04 | Indigenous Tourism BC Strategic Partnership 2025–2028 | Indigenous Tourism | AMBER | Active | 48 | Ministry of Indigenous Relations & Reconciliation | Finalize co-governance framework | 2026-08-01 | 2026-01-30 | RECR | Five-year partnership with Indigenous Tourism BC to double Indigenous-led tourism businesses, with $12M investment in capacity building, certification, and marketing.
T-I05 | Trans-Pacific Air Access Initiative (YVR Gateway) | Air Access | RED | Active | 30 | Ministry of Transportation & Infrastructure | MOU signed with target airline | 2027-03-31 | 2026-03-10 | TRANSPORT | Negotiate landing rights and incentive structures to attract 3 new non-stop routes connecting YVR to underserved Asia-Pacific and Latin American markets.
T-I06 | Rural & Small Community Tourism Support Program | Regional Development | GREEN | Active | 82 | Ministry of Tourism, Arts, Culture & Sport | Distribute Year 3 funding to 45 communities | 2026-05-30 | 2026-03-20 | ALL | $18M program providing grants and technical assistance to rural communities to diversify their tourism offerings and extend visitor seasons.
T-I07 | Hotel & Short-Term Rental Licensing Reform | Accommodation | AMBER | Active | 60 | Ministry of Housing / Local Government | Regulations tabled in fall 2026 sitting | 2026-11-15 | 2026-02-10 | ACCOM | Develop provincial framework for short-term rental licensing and data reporting to improve accuracy of accommodation supply and demand statistics.
T-I08 | BC Ferries Coastal Communities Tourism Connector | Transportation | GREEN | Active | 78 | BC Ferries Services Inc. | Launch 4 new coastal tourism packages | 2026-06-01 | 2026-03-05 | TRANSPORT | Partner with BC Ferries to develop 12 ferry-based tourism itineraries connecting coastal communities, targeting domestic and international visitors.

## EVIDENCE_LIBRARY
type | title | summary | author | publication_date | confidence_tag | source_tier | related_goal_id | related_initiative_id | link | related_subsectors
Data Release | BC Tourism Statistics 2024 Annual Economic Accounts | Annual report covering 2024 gross revenue ($23B), real GDP ($7.95B chained 2017$), employment (113.8K), wages ($5.03B), consumption taxes, and regional accommodation revenue. | BC Stats / Ministry of Finance | 2025-09-01 | high | official-curated | T-G01¦T-G03 | T-I03 | https://www2.gov.bc.ca/gov/content/data/statistics/economy/tourism | ALL
Research Report | Destination BC Visitor Research Report 2025: International Visitor Profile | Comprehensive survey-based analysis of international visitor motivations, spending patterns, satisfaction scores, and key source markets for BC. Includes post-COVID recovery benchmarks. | Destination BC | 2025-06-15 | high | official-curated | T-G02 | T-I01 | https://www.destinationbc.ca/content/uploads/ | ALL
Data Release | Statistics Canada Table 24-10-0055-01: Non-Resident Visitors Entering Canada via BC 2025 | Monthly counts of non-resident visitors entering Canada via British Columbia by country of residence, mode of transportation, arrival type, and traveller type. Full-year 2025 total: 8.36M. | Statistics Canada | 2026-02-15 | high | official-curated | T-G02 |  | https://www150.statcan.gc.ca/t1/tbl1/en/dtbl/dtblDnld/downloadDataset?pid=2410005501 | ALL
Research Report | BC Tourism Labour Force Needs Assessment 2024: Hospitality & Food Services Shortfall | Quantifies the estimated 18,000–22,000 FTE labour gap in BC hospitality, food services, and accommodation sectors. Projects growth to 2030 and recommends workforce retention policy levers. | Destination BC / Ministry of Labour | 2024-11-20 | medium | official-curated | T-G03 | T-I02 | https://www.destinationbc.ca/ | ACCOM¦FOODBEV
Policy Document | BC Indigenous Tourism Development Plan 2025–2030 | Five-year roadmap for tripling Indigenous-led tourism products and achieving $300M in Indigenous tourism revenue by 2030. Includes targets, governance, and investment frameworks. | Indigenous Tourism BC / Ministry of Indigenous Relations | 2025-03-01 | high | official-curated | T-G06 | T-I04 | https://www.indigenousbc.com/ | RECR
Research Report | UNWTO World Tourism Barometer 2025: Canada Outlook | Global and Canadian tourism recovery metrics showing full recovery to 2019 levels for most markets by end of 2024. BC highlighted as outperforming national averages on international arrivals. | UNWTO / Tourism HR Canada | 2025-01-20 | medium | official-curated | T-G01¦T-G02 |  | https://www.unwto.org/tourism-statistics/world-tourism-barometer | ALL

## RISKS_GAPS
risk_name | category | description | severity | likelihood | rag_status | owner | mitigation | last_reviewed | related_subsectors
US–Canada travel decline due to geopolitical tension | Market Access | US visitors represent 78% of BC's non-resident arrivals. Escalating trade disputes, tariffs, or travel advisories could substantially reduce US visitor volumes in 2026–2028. | HIGH | Likely | RED | Ministry of Tourism, Arts, Culture & Sport | Accelerate diversification to UK, Australia, Germany, Japan markets; increase domestic travel promotion; engage federal trade and diplomatic channels. | 2026-03-20 | ALL
Hospitality & food services labour shortage constraining growth | Workforce | Sector projected to need 22,000 additional FTE by 2028. Current shortfall limits hotel occupancy rates, restaurant hours, and quality of visitor experience in peak seasons. | HIGH | Likely | AMBER | Ministry of Labour / TACS | Phase II labour strategy; expand Temporary Foreign Worker Program for hospitality; partner with post-secondary institutions on accelerated pathways; retention bonuses. | 2026-02-20 | ACCOM¦FOODBEV
Unfavourable CAD/USD exchange rate reducing US visitor spending | Economic | A stronger CAD relative to USD reduces price competitiveness for American visitors. Current parity scenario could reduce per-visitor spending by 8–12% compared to 2024 levels. | MEDIUM | Possible | AMBER | BC Ministry of Finance | Monitor exchange-rate sensitive markets; adjust pricing strategies in collaboration with Destination BC; expand value-add packages. | 2026-01-15 | ALL
Climate disruption to seasonal tourism seasons | Environment | Increasing wildfire smoke, extreme heat events, and glacier retreat are reducing summer visitor confidence in Interior and Northern BC. Extended shoulder seasons may partially offset. | MEDIUM | Likely | AMBER | Ministry of Emergency Management | Develop sector-wide climate resilience playbook; diversify to shoulder-season and all-weather products; integrate climate risk into Destination BC marketing. | 2026-03-01 | RECR
YVR aviation capacity constraints limiting international growth | Infrastructure | YVR's landing slot allocations and terminal capacity may cap international flight growth before new route development. Airport expansion timeline uncertain to 2030. | MEDIUM | Possible | AMBER | Ministry of Transportation & Infrastructure | Advocate for federal airport infrastructure funding; explore secondary airports (Abbotsford, Kelowna) for charter relief; support YVR expansion planning. | 2026-02-10 | TRANSPORT
Short-term rental market distorting accommodation supply data | Data & Measurement | Lack of standardized reporting from platforms (Airbnb, VRBO) means true accommodation supply, occupancy rates, and revenue are underreported, affecting policy accuracy. | LOW | Likely | AMBER | Ministry of Housing | Implement mandatory STR licensing and reporting; integrate platform data into BC Stats tourism accounts; publish reconciled STR supply estimates annually. | 2025-12-15 | ACCOM