## Slide 1
LOOK WEST STRATEGY
Monitoring Dashboard & Data Workflow
A two-track work plan: trusted data → a single source of truth → an executive-ready dashboard
Work Plan · Draft v0.2 · June 2026
Owner: Mehdi Naji · For review & sign-off: Jacqueline (Director)

## Slide 2
OVERVIEW
What this plan covers
Look West Monitoring Dashboard & Data Workflow
2
01
The challenge & approach
Why monitoring needs one source of truth
02
Two parallel tracks
Data hub + dashboard & deployment
03
Metrics & governance
How metrics are proposed, validated, approved
04
Workflow & engagement
How the tracks connect; who we engage
05
Timeline to end of summer
Milestones, checkpoints, dependencies
06
Risks & next steps
Bottlenecks, mitigations, immediate actions

## Slide 3
CONTEXT
Where we are right now
Look West Monitoring Dashboard & Data Workflow
3
THE CHALLENGE
Look West progress data is fragmented
• Spread across public stats, internal spreadsheets, and announcements
• No single validated source of truth
• No executive-facing view of progress, gaps, or risks
• Metrics not yet defined or leadership-approved
ALREADY IN PLACE
Data Hub schema designed
13-table model: targets, trackers, announcements, reference data
Dashboard prototype built
HTML Monitor + 5 tracker pages (flexible design & UX)
Governance scaffolding
Ownership registry + dataset status & cadence
Not yet done
Metrics approval · validated data · deployment to users

## Slide 4
APPROACH
One rule: the Data Hub is the source of truth
Look West Monitoring Dashboard & Data Workflow
4
Data flows in one direction. Nothing is typed straight into the dashboard — every figure traces to a validated row in the Hub.
Sources
Public data · internal teams · announcements
Look West Data Hub
Validated · owned · governed — SOURCE OF TRUTH
Look West Monitor
Executive dashboard · progress, gaps, risks
Executives & users
Decision-ready, accessible
Why this matters: the long pole of the project is sourcing and validating data — not building the page.

## Slide 5
APPROACH
Two parallel tracks, one connection point
Look West Monitoring Dashboard & Data Workflow
5
WORKSTREAM 1
Data gathering, validation & Data Hub
Define a metric for each goal
Source from public / internal / announcements
Clean, standardize & validate with teams
Land it in the Hub as source of truth
Critical path
WORKSTREAM 2
Dashboard, reporting & deployment
Connect the dashboard to the Hub
Report progress, flag gaps & risks
Add BC economic context snapshot
Deploy securely with government IT
Follows the data
Both tracks meet at the Data Hub. Deployment with IT starts early, in parallel — not at the end.

## Slide 6
METRICS
How every metric is proposed & approved
Look West Monitoring Dashboard & Data Workflow
6
1
Draft
One metric per goal, using a standard template
2
Consult
Internal teams confirm it's meaningful & feasible
3
Revise
Refine based on team feedback
4
Approve
Leadership signs off (Jacqueline)
5
Populate
Locked into the Data Hub
FOR EACH PROPOSED METRIC WE DOCUMENT
What it measures
Why it's relevant
Does reliable data exist?
Public or internal source?
Update frequency
Limitations, gaps & risks

## Slide 7
GOVERNANCE
Checkpoints, approvals & who we engage
Look West Monitoring Dashboard & Data Workflow
7
FIVE CHECKPOINTS
CP1
Metrics consultation
Internal teams confirm feasibility
CP2
Leadership metric sign-off
Approved set locked into Hub · Jacqueline
CP3
Data validation
Each dataset validated, marked approved
CP4
Deployment go / no-go
Hosting, access & refresh · IT + Jacqueline
CP5
Executive review
Dashboard meets needs · continue / scale
WHO WE ENGAGE
Jacqueline · Director — approval
CP2 metrics · CP4 deploy · CP5 review
Daniel · Analyst — data input
Sourcing, cleaning, validation into the Hub
Nathan · Technical / IT advice
Hosting, security & deployment path (CP4)
Internal teams / SMEs · Validate & confirm
CP1 consultation · data validation
Mehdi · Project lead
Design, coordination, delivery, narrative

## Slide 8
WORKFLOW
One workflow, two deliverables
Look West Monitoring Dashboard & Data Workflow
8
Step
Checkpoint
Deliverable
Iteration ↻
Draft metrics
one per goal
CP1 · Consult
teams & SMEs
CP2 · Approve
metrics · Jacqueline
Source · validate
clean data (CP3)
★ DATA HUB
source of truth
Build dashboard
connect to Hub
CP4 · Deploy
IT go/no-go · Nathan
★ DASHBOARD
deployed to execs
CP5 · Review
executive feedback
↻ ITERATE — refresh data & metrics
↻ refine dashboard
A single flow with embedded checkpoints (CP1–CP5). Two iteration loops continuously refine the Data Hub and the dashboard.

## Slide 9
TIMELINE
A realistic path to end of summer
Look West Monitoring Dashboard & Data Workflow
9
IMMEDIATE
Weeks 1–2
Lock scope & draft metrics
Confirm dataset owners
Open IT / deployment talks
SHORT-TERM
Weeks 3–5
Consult teams (CP1)
Leadership sign-off (CP2)
First validated data in Hub
MEDIUM-TERM
Weeks 6–9
Populate Hub across domains
Build dashboard on real data
Deployment go/no-go (CP4)
END OF SUMMER
Weeks 10–12
Deploy to internal users
Executive review (CP5)
Iterate to refined v1
Checkpoints gate progress: CP1 → CP2 → CP3 → CP4 → CP5. Deployment depends on IT provisioning (start early).

## Slide 10
RISKS
Main bottlenecks & how we manage them
Look West Monitoring Dashboard & Data Workflow
10
Finding reliable data
Prefer public sources; allow internal/proxy metrics; flag gaps openly
Validating credibility
SME validation before any figure enters the Hub
Timely team input
Owner packets + biweekly check-ins; escalate when blocked
Leadership approval
Early consultation so sign-off is a confirmation, not a debate
Clean, reliable Hub
Controlled vocabularies, ownership, periodic clean-up
Deploying the dashboard
Engage government IT early, in parallel (key bottleneck)

## Slide 11
Immediate next steps
1
Confirm dataset owners
From the Workflow & Ownership Registry
2
Draft metrics per goal
Mehdi + Daniel, using the standard template
3
Open deployment talks
Nathan / government IT — start in parallel now
4
Schedule consultation (CP1)
Internal teams & SMEs confirm metrics
5
Book leadership sign-off (CP2)
Lock the approved metric set with Jacqueline
6
Stand up the cadence
Weekly internal sync + biweekly owner check-ins
Target: process streamlined and dashboard deployed by end of summer.